Proposal for Foreign Assistance

Submitted to the Social Welfare Council, Government of Nepal

A) NGO description

a) Name of the organization: "Campaign for education"

b) Address: Dillibazar, Kathmandu-33.

c) Contact person: Mr. Bidur Dhungana, an advocate at the Supreme Court is the primary contact person.

d) Main objective: We wish to work with the children to help them go to school. We primarily help those children who would otherwise not go to school without some form of financial assistance. We also help the children get some form of training so that they are self employed. Our assistance is limited to scholarships to cover the tuition fees, uniform and books and supplies. We focus on girls, marginalized communities and orphans.

e) CE was registered with Kathmandu CDO on 2062/6/12 registered no .191/062/063

f) Affialition number: 18733

B) Project Details

1) Name of the project:  Campaign for Education year 2

2) Project locations

We plan to operate in the following areas:

| Area | Students | Schools |
| --- | --- | --- |
| Kathmandu municipality wards no 10, 16, 29 | Ujeli Bhujel , Rojina Rajthala, Sumaiya Nepali , Surakshya Dhakal, Ojina Rajthala, Kumar Tamang, Ansu Shrestha | Paropakar Secondary School , Kalimati; Shree Om School , Gausala; Guheshowri School , Thapathali |
| Patan Sub Municipality ward no 11 | Kopila Karki, Dinesh Acharya, Sabina Sapkota, Pradeep Lama, Laxmi Shrestha, Dinesh Basnet, Laxmi Sunuwar, Sharmila Tandukar, Lapsang Lama, Pramila Humagain, Kripa Pokharel, Pragya Pokharel, Prasamsa Pokharel | Viswa Niketan Higher Secondary School, Namuna Machindra Madhyamik Vidhyalaya, Mangal Boarding School, Annapurna Boarding School, Shree Min Nath Adarsha Siksha Sadan |
| Kavre, Rabiopi VDC | Santosh Bhujel, Ram Kumar Mijar, Subin Bogati, Shyam thapa, Sarada Thapa, Sunita Thapa | Ganga Devi secondary School |
| Nepalgung municipality 19 | Usha Thapa,Sonal Gharti, Shiva Thapa, Milina Khatri, Hastanath Yogi, dhanmaya sunar, jyoti sharma, puja singh, sujal khanal,rabisha banskota, kalpana acharya, Sushila Chaudhary, Manish Karki, Hina Manihar,Pabitra Dhungana, Trishna Chand Thakuri,Puja Khatri,Nisha Verma,Ganga Adhikari | Gyan Sagar High School, Rani Talau Primary School, Mangal Prasad M. P. High School, Rani Talau Primary School, Shree Dhamboji Secondary School |
| Palpa, Madan pokhara VDC | Tilishara Somai, Bishnukumari Chidi, Sushma Nepali, Rita Nepali, Rekha Thadarai, Tilak Rana, kavita nepali, sharmila khatri, mana kumari masrangi , bina gaire | Bhagwati Middle Secondary School, Bhagwati Middle Secondary School, Sharada Higher Secondary School, Sharada Higher Secondary School, Sharada Higher Secondary School, Bhagwati Middle Secondary School |

3) Project start and end dates

Starting date   June  2007

End date  May 2008

4) This will  be a continuing  project.

5) Project Sector: Education

We focus on children; we focus girls, marginalized communities and orphans.

6) Project Selection Criteria

Background

Nepal has one of the lowest school enrolment rates for the children who are supposed to go to school.  An informal survey of a school near Kavre indicated that almost 80% of the students drop out from school before high school. The pass rate in the annual SLC exam is very low.

Problems identified in the project areas

We have identified that many of the children do not attend school because of financial reasons. Even if they attend, they will not complete the course or fail the class because they don't have enough of books and supplies.  And they are not monitored while in school, so for those who are in school also don't know where they are going.

We select project areas based on the answers to the following questions. These are the questions a potential area coordinator would have to answer before being appointed as an area coordinator.

- What is the estimation on number of children who do not go to school in your area? - Why do they not go to school? Give specific examples. - To which ethnic groups do these students belong? - When do students typically drop out of school and why? Before or after SLC? Give specific examples. - What is the total school-related cost (fees, uniform, books and stationeries) per student in that area? - What is the typical family income of these students? What is their main source of income? - What are the chances that you might move from your area to elsewhere in the next two years? - How many volunteers do you think you can recruit? - Do you have regular (a few times a week) email access?

We communicate with the local volunteers and ask them to send us answers to the above questionnaire and once we get a satisfactory answer we approve the area for operation.

After we select an area, we call for application. For each application, we score on the basis of its quality. Here is our scoring system

| Criteria | Score |
| --- | --- |
| Female applicant | 7 |
| Orphan | 5 |
| Marginalized community( dalit) | 5 |
| Uneducated parents | 3 |
| Academic excellence | 2 |
| Not gone to school last year | 5 |

All the applicants should meet the following family income criteria:

| Number of children | # Family income (per month) for Urban areas in Rs | # Family income (per month) for Rural areas in Rs |
| --- | --- | --- |
| 1 | 2500 | 1500 |
| 2 | 2800 | 1700 |
| 3 | 3100 | 1900 |
| 4 or more | 3400 | 2100 |

Once we select a student, we do not give the money directly to the student. Our volunteer pays the school fees and buys the supplies and the uniform. We limit our financial assistance to a maximum of Nrs 7500 per student per year.

7) Objectives of the project

The main objective of the project is to help the children we select to continue and succeed in school. For this we help with the tuition, supplies and uniforms. We also help them stay at school by monitoring them monthly with the help of our volunteers. We monitor their attendance at school, performances at school, performance at extra curricular activities. We get this information from the school, teachers, parents, in addition to the information from the student herself. We review monthly reports to judge the students    performance so that we can renew the financial assistance.

8) Activities

Our area coordinators recruit a local team of volunteers who visit our sponsored students monthly to make sure our students are coming to school regularly and are making satisfactory progress. Our volunteers stay in contact with the teachers and the parents to address any needs of our children. The grant money is never given directly to the students or their families - our volunteers directly pay the school fees and buy books, stationeries, and uniform for the students. We also organize occasional extra curricular activities for the students we have sponsored.

9) Project Implementation process.

The students who are selected are sent to school and their expenses are covered for a maximum of  NRs 7500 per student. These expenses are paid directly by our volunteers. Then these students are regularly followed up for their attendance, performance in exam and extra curricular activities.  We do this level of monitoring every month and review the reports periodically. At the end of the year they are expected to pass the class. If they fail, the financial assistance is terminated.  If they pass and meet the income criteria, their financial assistance is renewed.

10) Target group and number of beneficiaries

The target group is the school age children of the areas we have selected.

The number of beneficiaries for this year is limited to total of 60 children in the areas mentioned above.

11) Expected outcome

Short term: We expect all 60 students to complete the grade and be promoted to the next grade.

Long term: We expect them to see that they have become responsible citizens of the country.

12) Links with other agencies

We will be working being linked to different governmental and non governmental agencies. We agree to be monitored by social welfare council. We will also comply with the local rules and coordinate with district education office.

13) Status report

Since this is our starting year, we do not have any monitoring and evaluation report

Status report will be submitted at the end of each academic year, normally June of the year. This will be submitted to the Donor agency, the SWC and the local governmental bodies (the VDC/municipality, the district education office) for the year 2007/2008, the report will be submitted in June 2008.

14) Stability of the project

We provide financial assistance to students who are unable to go to school or are about to drop out of school due to financial reasons. Our goal is to enroll the students and keep them in school until they complete 12th grade or the Intermediate level. Until a child is no longer deprived of education due to financial reasons, our project will continue.

15) Calendar of operation

Feb 2007: collection of applications

March 2007: Selection of students

June 2007: distribution of scholarships

Monthly reports from June 2007 till June 2008.( 12 reports)

Final report on June 2008

C) Financial details

1) The assistance will be in the form of financial grant towards providing scholarship to the needy children.

2) Nepal children education fund (NCEF) in the United States is the primary donor agency. NCEF is located in Cambridge, MA 02238 USA, email contact@nepalchildren.org

It will sponsor the costs of the students and the amount will be limited to about $6000 a year. This will primarily depend on the number of areas and the students selected.

3) There will be  minimal  internal source.

4) Total costs would be

Administrative cost

Program cost

5) Details of the annual budget breakdown.

| Description | ## Amount |
| --- | --- |
| School fees | 4,50,000.00 |
| Conveyance/travel | 7,500.00 |
| Stationery,printing, | 6,000.00 |
| Guests,teas,snacks | 5,000.00 |
| Office rent | 18, 000.00 |
| Telephone | 4,000.00 |
| Electricity | 1,800.00 |
| Miscellaneous/contingencies | 20,700.00 |
| Total | 5,13,000.00 |
| CE internal resources | 1,40,000.00 |
| Amount requested from | 3,73, 000.00 |

D) Personnel

Number of local volunteers: 25

E) Bank details

Nepal Bangladesh bank main branch office, Bijuli Bazar

Account number 118601S

Submitted by

Bidur Dhungana

Working as Secretary  with CE

Dated  May 30, 2007

### Progress report for 2007

Campaign for education is a NGO registered with CDO Kathmandu. We wish to work with the children to help them go to school. We primarily help those children who would otherwise not go to school without some form of financial assistance. We also help the children get some form of training so that they are self employed. Our assistance is limited to scholarships to cover the tuition fees, uniform and books and supplies. We focus girls, marginalized communities and  orphans.

Our short term objective for 2007 was to help all of our students to pass the current grade and move to the next grade. Barring one, all of them passed the class which is a significant achievement.

Following is the list of students who passed the class:

| Area | Students |
| --- | --- |
| Kathmandu | Ujeli Bhujel , Rojina Rajthala, Sumaiya Nepali , Surakshya Dhakal, Ojina Rajthala, Kumar Tamang, Ansu Shrestha |
| Palpa | Kavita Nepali, Sharmila Khatri, Mana Kumari Masrangi , Bina Gaire |
| Nepalgunj | Dhanmaya Sunar, Jyoti Sharma, Puja Singh, Sujal Khanal, Rabisha Banskota, Kalpana Acharya, Sushila Chaudhary, Manish Karki, Hina Manihar,Pabitra Dhungana, Trishna Chand Thakuri,Puja Khatri,Nisha Verma |
| Patan | Dinesh Basnet, Laxmi Sunuwar, Sharmila Tandukar, Lapsang Lama, Pramila Humagain, Kripa Pokharel, Pragya Pokharel, Prasamsa Pokharel |
| Kavre | Santosh Bhujel, Subin Bogati, Ram Mrijar, Shradha Thapa, Shyam Thapa, Sunita thapa |

Ganga Adhikari from Nepalgunj failed the class and hence her sponsorship is terminated.

We have recieved monthly reports from all the areas with all the students. The reporting has  been satisfactory with an average of 75%

We enclose a seperate Audit report for the fiscal year 2062/2063.

This concludes our report for the academic year 2006/2007.